# Project Estimation: GitLab-based Application Evergreening Engine

This document outlines the tasks, estimations, and assignments for building the Maven and Gradle-based automated dependency upgrade pipelines in GitLab CI/CD. The project will be delivered by 3 senior developers and 1 tech lead.

# Team Roles

- Lead Engineer: Oversees architecture, GitLab integration strategy, code reviews

- Senior Developer 1: Maven pipeline implementation

- Senior Developer 2: Gradle pipeline implementation

- Senior Developer 3: Shared scripting, utilities, documentation

# Task Breakdown & Estimations

| Task | Owner | Estimation |
| --- | --- | --- |
| Design pipeline structure and CI strategy | Lead | 2 days |
| Set up GitLab common repo and configure templates | Lead | 1 day |
| Implement Maven upgrade pipeline (.gitlab-ci.yml + scripts) | Senior Dev 1 | 3 days |
| Implement Gradle upgrade pipeline (.gitlab-ci.yml + scripts) | Senior Dev 2 | 3 days |
| Create shared bash scripts and utility functions | Senior Dev 3 | 2 days |
| Implement PR creation using GitLab API | Senior Dev 3 | 2 days |
| Test Maven pipeline in sample repo | Senior Dev 1 | 1 day |
| Test Gradle pipeline in sample repo | Senior Dev 2 | 1 day |
| Add documentation and onboarding guide | Senior Dev 3 | 1 day |
| Code review and final integration | Lead | 2 days |

# Timeline Estimate

Estimated project duration: **10–12 working days**

Includes time for testing, code review, and documentation.

# Notes

- Tasks may run in parallel where possible.

- Coordination between developers will be needed for shared scripts and testing.

- Post-deployment support or enhancements can be tracked separately.